## Jobs
Construction cash flow template
VIABUILD · https://www.viabuild.au/resources/construction-cash-flow-template · Last reviewed 28 September 2026
Job | Contract value ex GST | GST | Contract value inc GST | Stages | Claimed to date ex GST | Left to claim ex GST
Job A (example: replace)

## Claims in
Construction cash flow template: claims in
VIABUILD · https://www.viabuild.au/resources/construction-cash-flow-template · Last reviewed 28 September 2026
Job | Stage or claim | Claim amount ex GST | GST | Claim total inc GST | Date submitted | Payment terms (days) | Usual extra days | Expected payment date | Date received

## Money out
Construction cash flow template: money out
VIABUILD · https://www.viabuild.au/resources/construction-cash-flow-template · Last reviewed 28 September 2026
Job | Supplier or subcontractor | Reference | Amount ex GST | GST | Total inc GST | Retention held | Due date | To pay on due date | Date paid | Retention release date | Retention released on

## Weekly forecast
Construction cash flow template: weekly forecast
VIABUILD · https://www.viabuild.au/resources/construction-cash-flow-template · Last reviewed 28 September 2026
Settings
Forecast start |  | The Monday of week one.
Opening bank balance |  | What is in the bank that day, read from the bank.
Low-balance threshold |  | The balance below which you want a week flagged. It is your number, set by what your business needs to carry.
GST rate | 10% | Used by every GST column. Set at ten per cent; confirm the rate that applies to your work with your accountant.
Week | Week starting | Opening balance | Claims in | Other cash in | Bills out | Retention released | Other cash out | Closing balance | Low balance
1
2
3
4
5
6
7
8
9
10
11
12
13

## Instructions
Construction cash flow template: instructions
VIABUILD · https://www.viabuild.au/resources/construction-cash-flow-template · Last reviewed 28 September 2026
Five sheets. Shaded cells are for typing in; every other figure is a formula, so the forecast fills itself in from what you enter. The job name is the thread that ties the sheets together, so type it the same way every time.
How to use it
1. List every live job | One row per job on the Jobs sheet, with the current contract value excluding GST and the claim stages as the contract names them. Overwrite the example row. The job name you type here is the one the other sheets must match.
2. Enter every claim in the next thirteen weeks | Claims already sent, and claims the programme says you will send. For each one, the date it goes out, the payment terms from the contract, and the extra days this client actually takes. The expected payment date works itself out, and it is the receipt date, not the invoice date.
3. Enter every bill and subcontract claim by due date | Supplier invoices and trade claims on the Money out sheet, each with the date it falls due under its terms. Where you withhold retention, enter the amount held and the release date the subcontract sets, so the release lands in the week it is owed.
4. Set the start, the opening balance and your threshold | At the top of the Weekly forecast sheet: the Monday the forecast starts, the balance actually in the bank that day, and the balance below which you want a week flagged. The threshold is yours to set; the template does not suggest one.
5. Add the cash out the jobs do not show | Wages, rent, insurances, vehicle and loan repayments, and the BAS remittance in the week it falls due, in the Other cash out column. These land whether the jobs claim or not, and a forecast without them flatters the position.
6. Read it weekly, and move it when the programme moves | Update the opening balance, mark what was received and paid, and read the flag. When a stage slips, move the claim date behind it the same day; the supplier payments mostly will not move with it.
Jobs sheet
Job | The job name or address, one row per live job. The first row reads Job A (example: replace); overwrite it.
Contract value ex GST | The current contract sum excluding GST, with approved variations included.
GST | Worked out from the GST rate on the forecast sheet.
Contract value inc GST | The two added together.
Stages | The claim stages as the contract's claim schedule names them, typed as text.
Claimed to date ex GST | Added up from the Claims in sheet for this job.
Left to claim ex GST | The contract value less what has been claimed.
Claims in sheet
Job | Exactly as it is written on the Jobs sheet, so the claimed-to-date total finds it.
Stage or claim | The stage in the contract's words, or the variation number.
Claim amount ex GST | The amount claimed, excluding GST.
GST | Worked out from the GST rate on the forecast sheet.
Claim total inc GST | The amount that should reach the bank.
Date submitted | The day the claim goes out, or for a claim not yet sent, the day the programme says the stage will be claimed.
Payment terms (days) | From the contract, not from a template.
Usual extra days | How many days beyond the terms this client actually takes to pay. Leave it blank if they pay on time.
Expected payment date | The date submitted plus the terms plus the usual extra days. This is the date the forecast uses.
Date received | Filled in when the money lands. A received claim drops out of the forecast, because it is already in the bank balance.
Money out sheet
Job | The job the bill belongs to.
Supplier or subcontractor | Who is owed.
Reference | The invoice, claim or purchase order number.
Amount ex GST | The bill excluding GST.
GST | Worked out from the GST rate; type over it for a bill that carries no GST.
Total inc GST | The bill as it will be paid, before retention.
Retention held | Any amount withheld from this payment, as the subcontract provides for.
Due date | The date the bill falls due under its terms.
To pay on due date | The total less any retention held.
Date paid | Filled in when it is paid. A paid bill drops out of the forecast.
Retention release date | The trigger date the subcontract sets for releasing what was held, diarised the day the retention is withheld.
Retention released on | Filled in when it is released. Until then it stays in the forecast as cash out in the week it is owed.
Weekly forecast sheet
Four settings at the top, then thirteen weeks. Week one also picks up anything overdue: a claim past its expected payment date that has not arrived, or a bill past its due date that has not been paid.
Forecast start | The Monday of week one.
Opening bank balance | What is in the bank that day, read from the bank.
Low-balance threshold | The balance below which you want a week flagged. It is your number, set by what your business needs to carry.
GST rate | Used by every GST column. Set at ten per cent; confirm the rate that applies to your work with your accountant.
Week | One to thirteen.
Week starting | Worked out from the forecast start.
Opening balance | The opening bank balance in week one, then the previous week's closing balance.
Claims in | Every claim not yet received whose expected payment date falls in the week, including GST.
Other cash in | Typed in: anything else expected in the week, such as the deposit on a newly signed contract.
Bills out | Every unpaid bill due in the week, less any retention held.
Retention released | Every retention not yet released whose release date falls in the week.
Other cash out | Typed in: wages, rent, insurances, loan repayments and the BAS remittance, in the week each one lands.
Closing balance | The opening balance plus cash in, less cash out.
Low balance | Shows LOW when the closing balance is under your threshold.
Common traps
Claim dates copied from the invoice | A forecast that books the money on the day the claim is issued ignores the payment terms and the client’s actual habits. The template asks for both so the claim lands in the week the money realistically arrives.
The forecast not moved with the programme | A stage slips a fortnight and the claim behind it slips a fortnight, while the bills for that stage mostly do not. A forecast still carrying the old dates is wrong in the direction that hurts, and it stays wrong quietly.
GST read as money you can spend | The GST collected on a claim sits in the account until the BAS falls due. The template forecasts in bank terms, GST included, so the remittance has to be entered as cash out in its own week or the balance between BAS dates overstates what the business can spend.
Overheads left out | Wages, rent and repayments land every week whether the jobs claim or not. A forecast built only from the jobs shows a healthier business than the one that has to make payroll.
Retention forgotten at the tail | Retention you hold on trades is a payable with a release date, and retention held on you is a receivable nobody sends an invoice for. Both need a date and an owner, or one surprises the position and the other quietly becomes a write-off.
The new deposit funding the old job | A deposit makes the balance look healthy, but it belongs to work not yet built. Spending it to cover another job’s dip works once per job and leaves a bigger hole, which is the pattern a rolled-up forecast exists to show early.
Not financial or tax advice.