## Site diary
Site diary template
VIABUILD · https://www.viabuild.au/resources/site-diary-template · Last reviewed 20 September 2026
Date, job and author | Weather, and what it did to the work | Trades on site | Deliveries and materials | Delays and disruptions | Instructions and decisions | Inspections and visitors | Progress and photos

## Field guide
Site diary template: what each field records
VIABUILD · https://www.viabuild.au/resources/site-diary-template · Last reviewed 20 September 2026
Field | What it records
Eight fields, the same ones every day. The test of an entry is whether someone reading it in three years, with no memory of the job, could reconstruct the day from it.
Date, job and author | Who wrote the entry and when. An unsigned, undated note is an anecdote. The author matters because the entry is that person's account of a day they were present for, which is what gives it standing.
Weather, and what it did to the work | Morning and afternoon conditions, and the effect: whether trades could proceed, what stopped, who was stood down. "Rain" is a fact about the sky; "site closed, slab pour cancelled, concreter stood down" is a fact about the job, and only the second one supports a claim.
Trades on site | Which companies, how many people, what they worked on. This is what later shows a stage was progressing, a trade was delayed by others, or a disruption cost real labour, rather than asserting it without support.
Deliveries and materials | What arrived, what was short or damaged, and what failed to turn up. A late delivery that stalls a trade is a programme event, captured while the docket and the memory are both fresh.
Delays and disruptions | Anything that stopped or slowed work, and why: the trade that did not show, the failed inspection, the access problem, the design query holding a stage. These entries are what connect a cause to a programme impact when a delay has to be justified.
Instructions and decisions | Anything directed, agreed or decided on site, and by whom. The change directed verbally and never recorded is the classic source of a disputed variation, and this field is where the conversation is captured before it becomes a disagreement.
Inspections and visitors | Who came to site, what they looked at and what resulted: the certifier, the engineer, the client walking their own build. The inspection that passed, and what it covered, is evidence the job will want later.
Progress and photos | What was completed, tied to dated photographs, including what is about to be covered up. The photo of what was under the slab, taken before the pour, settles arguments nothing else can.
General information, not legal advice.