## Variation register
Variation register template
VIABUILD · https://www.viabuild.au/resources/variation-register-template · Last reviewed 20 September 2026
Variation number | Date identified | Source | Description | Cost and margin | Time effect | Status | Approval evidence | Contract-sum impact | Claim status

## Column guide
Variation register template: what each column records
VIABUILD · https://www.viabuild.au/resources/variation-register-template · Last reviewed 20 September 2026
Column | What it records
Ten columns. A register that carries all of them can answer any question the job, the client or a dispute will ask of it. A register missing one will fail at exactly the moment that column was needed.
Variation number | Sequential per job, assigned when the change is identified, never reused. The number is what lets a claim line, an email and a signed document all point at the same change without ambiguity.
Date identified | The day the change entered the job, not the day it was priced. The gap between this date and the approval date is the builder financing the change, and the register is the only place that gap is visible.
Source | Client request, site condition, documentation gap or authority requirement. Who chose the change shapes the conversation, and a register that records source shows patterns, the job where the documents were thin, the client whose selections keep moving. Where the source was a documentation gap, the variation usually began life as a question, which is why the RFI register and this one are worth keeping side by side.
Description | Precise enough that someone who was not in the conversation could price it: what is added, what is omitted, what is substituted, against which drawings. Most variation disputes are really description disputes.
Cost and margin | The build-up behind the price, and the margin applied at the rate the contract's variation clause allows. The client sees the price; the register keeps the working, so the number can explain itself months later.
Time effect | The days the change adds to the programme, claimed through the contract's extension of time machinery rather than assumed. A variation priced without its time has quietly shortened the build period for free.
Status | Identified, priced and sent, approved, declined, claimed, paid. The status ladder below. A register whose statuses are current is a management tool; one updated monthly is an archaeology project.
Approval evidence | A reference to the signed document, the recorded portal approval or the dated written instruction. The register row is the index entry; the evidence is what wins the argument.
Contract-sum impact | The signed amount, positive or negative, because omissions are variations in the other direction and deserve the same discipline. Summed with the original contract sum, this column is the current contract value, which is also the figure home warranty notification questions are asked against.
Claim status | Which progress claim the variation was billed on, and whether it has been paid. Approved but never claimed is the quietest way to lose margin, and this column is where it shows up before the final account.
General information, not legal advice.